## shoshin_phase4_all_tasks
Task ID | Sprint | Epic | Feature | Task Description
TASK-001 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Identify all existing Character WPForms field IDs for stats and metadata
TASK-002 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field game_system to Character form (final step)
TASK-003 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_melee_damage to Character form
TASK-004 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_melee_crit to Character form
TASK-005 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_melee_distance to Character form
TASK-006 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_ranged_damage to Character form
TASK-007 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_ranged_crit to Character form
TASK-008 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_ranged_distance to Character form
TASK-009 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_atk to Character form
TASK-010 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_def to Character form
TASK-011 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_mov to Character form
TASK-012 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_bod to Character form
TASK-013 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_ldr to Character form
TASK-014 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_ini to Character form
TASK-015 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_total_cost to Character form
TASK-016 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Add hidden field char_mrbpa_modifiers to Character form
TASK-017 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Update Character JS to set game_system = 'Path of Ascension' on init or submit
TASK-018 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Update Character JS to write melee damage/crit/distance into hidden fields
TASK-019 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Update Character JS to write ranged damage/crit/distance into hidden fields
TASK-020 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Update Character JS to write ATK/DEF/MOV/BOD/LDR/INI into hidden fields
TASK-021 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Update Character JS to write total cost into char_total_cost
TASK-022 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Implement MRBPA aggregation and write to char_mrbpa_modifiers
TASK-023 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Test saving new character and confirm all hidden fields populate correctly
TASK-024 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.1: Character Hidden Stat Fields | Test editing character (changing options) and confirm hidden fields stay in sync
TASK-025 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Identify Support Asset WPForms field IDs for Ozutsu and Mokuzo stats
TASK-026 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field game_system to Support Asset form (final step)
TASK-027 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_melee_damage to Support Asset form
TASK-028 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_melee_crit to Support Asset form
TASK-029 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_melee_distance to Support Asset form
TASK-030 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_ranged_damage to Support Asset form
TASK-031 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_ranged_crit to Support Asset form
TASK-032 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_ranged_distance to Support Asset form
TASK-033 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_atk to Support Asset form
TASK-034 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_def to Support Asset form
TASK-035 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_mov to Support Asset form
TASK-036 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_bod to Support Asset form
TASK-037 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_ldr to Support Asset form
TASK-038 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_ini to Support Asset form
TASK-039 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_total_cost to Support Asset form
TASK-040 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Add hidden field asset_mrbpa_modifiers to Support Asset form
TASK-041 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Update Support JS to set game_system = 'Path of Ascension' on init or submit
TASK-042 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Update Support JS to write Ozutsu ranged stats into hidden fields
TASK-043 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Update Support JS to write Mokuzo hull-derived stats into hidden fields
TASK-044 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Update Support JS to write ATK/DEF/MOV/BOD/LDR/INI into hidden fields
TASK-045 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Update Support JS to write asset_total_cost into hidden field
TASK-046 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Implement MRBPA aggregation and write to asset_mrbpa_modifiers
TASK-047 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Test Ozutsu entry and confirm all hidden fields populate correctly
TASK-048 | Sprint 1 | Epic 1: Derived Stat Persistence | Feature 1.2: Support Asset Hidden Stat Fields | Test Mokuzo entry and confirm all hidden fields populate correctly
TASK-049 | Sprint 1 | Epic 2: /my-assets Inventory | Feature 2.1: /my-assets Table and Grouping | Create /my-assets page template or shortcode container
TASK-050 | Sprint 1 | Epic 2: /my-assets Inventory | Feature 2.1: /my-assets Table and Grouping | Implement query for Character WPForms entries for current user
TASK-051 | Sprint 1 | Epic 2: /my-assets Inventory | Feature 2.1: /my-assets Table and Grouping | Implement query for Support Asset WPForms entries for current user
TASK-052 | Sprint 1 | Epic 2: /my-assets Inventory | Feature 2.1: /my-assets Table and Grouping | Implement grouping for Characters by class (Daimyo through Onmyoji)
TASK-053 | Sprint 1 | Epic 2: /my-assets Inventory | Feature 2.1: /my-assets Table and Grouping | Implement grouping for Support Assets by type (Artillery, Sailing Ships, Other)
TASK-054 | Sprint 1 | Epic 2: /my-assets Inventory | Feature 2.1: /my-assets Table and Grouping | Sort assets within each group by Reference ID descending
TASK-055 | Sprint 1 | Epic 2: /my-assets Inventory | Feature 2.1: /my-assets Table and Grouping | Build HTML table headers for Image, Ref ID, Melee, Ranged, Stats, Cost, Actions
TASK-056 | Sprint 1 | Epic 2: /my-assets Inventory | Feature 2.1: /my-assets Table and Grouping | Map Character entries into table rows using hidden stat fields
TASK-057 | Sprint 1 | Epic 2: /my-assets Inventory | Feature 2.1: /my-assets Table and Grouping | Map Support Asset entries into table rows using hidden stat fields
TASK-058 | Sprint 1 | Epic 2: /my-assets Inventory | Feature 2.1: /my-assets Table and Grouping | Ensure melee/ranged distances and MOV render with inch symbol
TASK-059 | Sprint 1 | Epic 2: /my-assets Inventory | Feature 2.1: /my-assets Table and Grouping | Implement placeholder image logic for assets without a defined image
TASK-060 | Sprint 1 | Epic 2: /my-assets Inventory | Feature 2.1: /my-assets Table and Grouping | Add Assign (green), Edit (yellow), Delete (red) action buttons to each row
TASK-061 | Sprint 1 | Epic 2: /my-assets Inventory | Feature 2.1: /my-assets Table and Grouping | Test /my-assets layout, grouping, and sorting with mixed asset data
TASK-062 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Add hidden HTML container for Assign modal on /my-assets page
TASK-063 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Implement JS to open Assign modal when Assign button is clicked
TASK-064 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Render asset display box inside modal using existing summary HTML/CSS
TASK-065 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Implement AJAX endpoint to return user's roster list
TASK-066 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Populate 'Select Clan Roster' dropdown in modal from AJAX data
TASK-067 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Add numeric quantity input (1â€“99) to Assign modal
TASK-068 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Style Assign button green and Cancel button red in modal
TASK-069 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Implement AJAX endpoint to add asset to selected roster
TASK-070 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | On server, load target roster and parse roster_items_json
TASK-071 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | If asset is non-Daimyo, merge or append roster item with quantity
TASK-072 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Detect when assigned asset is a Daimyo type
TASK-073 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Count existing Daimyo items in roster from roster_items_json
TASK-074 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Return flag to client when a Daimyo conflict exists
TASK-075 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | In JS, show Daimyo replacement prompt when conflict flag is returned
TASK-076 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Implement second AJAX call to perform Daimyo replacement when confirmed
TASK-077 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | On server, remove all existing Daimyo items from roster_items_json
TASK-078 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Insert new Daimyo roster item with requested quantity
TASK-079 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Recompute roster_total_points from updated roster items and asset costs
TASK-080 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Save updated roster back to WPForms with new JSON and total points
TASK-081 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | On client, close modal and show assignment success notification
TASK-082 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Test assigning non-Daimyo asset to multiple rosters
TASK-083 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Test assigning first Daimyo to an empty roster
TASK-084 | Sprint 2 | Epic 2: /my-assets Inventory | Feature 2.2: Assign Modal and Daimyo Logic | Test assigning second Daimyo and validate replacement flow works correctly
TASK-085 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.1: Roster Form Shell (/create-roster) | Create WPForms form for Create Clan Roster
TASK-086 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.1: Roster Form Shell (/create-roster) | Add visible roster_name field (required)
TASK-087 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.1: Roster Form Shell (/create-roster) | Add visible roster_ref_id field with placeholder (required)
TASK-088 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.1: Roster Form Shell (/create-roster) | Add hidden owner_user_id field to roster form (final step)
TASK-089 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.1: Roster Form Shell (/create-roster) | Add hidden roster_items_json field to roster form
TASK-090 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.1: Roster Form Shell (/create-roster) | Add hidden roster_total_points field to roster form
TASK-091 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.1: Roster Form Shell (/create-roster) | Add HTML block placeholder for Roster Composition UI
TASK-092 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.1: Roster Form Shell (/create-roster) | Implement JS or PHP hook to populate owner_user_id on form render
TASK-093 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.1: Roster Form Shell (/create-roster) | Test creating and saving a minimal roster entry without items
TASK-094 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Implement JS to load all user assets for use in roster composer
TASK-095 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Group assets into dropdown optgroups by class and support type
TASK-096 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Render asset <select> element, quantity input, and 'Add to Roster' button
TASK-097 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Initialize in-memory rosterItems array for selected units
TASK-098 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | On Add click, validate asset selection and quantity range
TASK-099 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Enforce max 1 Daimyo per roster in JS when adding units
TASK-100 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Insert new roster item or update existing roster item in rosterItems array
TASK-101 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Render roster items table showing asset label, type, qty, unit cost, line total
TASK-102 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Implement Remove action to delete items from rosterItems array
TASK-103 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Compute Clan Points total from rosterItems and hidden asset costs
TASK-104 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Compute Initiative total from asset initiative values
TASK-105 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Compute Total Honor (XP) from asset leadership values
TASK-106 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Compute Masteries as floor(ClanPoints / 125)
TASK-107 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Display Clan Points, Initiative, Total Honor, and Masteries in composer UI
TASK-108 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Write serialized rosterItems JSON into hidden roster_items_json field
TASK-109 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Write updated roster_total_points value into hidden field
TASK-110 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Detect empty asset list and show 'no assignable units' message
TASK-111 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Add Create Character and Create Support Asset buttons to empty-state message
TASK-112 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Include notice that leaving will not create Clan Roster in empty-state UI
TASK-113 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Test adding, editing, and removing units and confirm JSON matches UI
TASK-114 | Sprint 2 | Epic 3: Clan Roster Creation | Feature 3.2: Roster Composer UI & Live Totals | Test saving and re-editing roster, rebuilding composer UI from JSON
TASK-115 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Create /my-rosters page template or shortcode container
TASK-116 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Query roster WPForms entries for the current user
TASK-117 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Parse roster_items_json for each roster entry
TASK-118 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Fetch referenced asset entries for each roster item as needed
TASK-119 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Compute Clan Points per roster from asset costs and quantities
TASK-120 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Compute Initiative total per roster from asset initiative stats
TASK-121 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Compute Total Honor (XP) per roster from asset leadership stats
TASK-122 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Compute Masteries as floor(ClanPoints / 125) for each roster
TASK-123 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Count Daimyo, Samurai, Ashigaru, Sohei, Ninja, and Onmyoji units per roster
TASK-124 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Count total Support Assets (Artillery and Sailing Ships) per roster
TASK-125 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Build summary table headers including points, initiative, honor, and counts
TASK-126 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Render one summary row per roster with computed values
TASK-127 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Add expandable '+' button at start of each roster row
TASK-128 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Render hidden expanded row containing composition table per roster
TASK-129 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Populate composition table with Class â€” Ref ID, Type, Qty, unit cost, line total
TASK-130 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Add Edit button to navigate to roster edit form for that roster
TASK-131 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Add Delete button (red) for roster deletion (logic implemented later)
TASK-132 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Add Print button placeholder to trigger print selector (wired in Sprint 4)
TASK-133 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.1: /my-rosters Summary Table | Test /my-rosters with multiple rosters and verify calculations are correct
TASK-134 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.2: Roster Limits by Role | Define mapping of WordPress roles to roster limits (Contributor, Author, etc.)
TASK-135 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.2: Roster Limits by Role | Implement helper function to determine max roster count for current user
TASK-136 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.2: Roster Limits by Role | Before creating a new roster, count existing rosters for that user
TASK-137 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.2: Roster Limits by Role | Block roster creation when user already meets or exceeds their limit
TASK-138 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.2: Roster Limits by Role | Display clear message when roster creation is blocked due to role limit
TASK-139 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.2: Roster Limits by Role | Optionally show roster limit info note on /my-rosters page
TASK-140 | Sprint 3 | Epic 4: Roster Dashboard & Limits | Feature 4.2: Roster Limits by Role | Test roster limits with test users in Contributor and Author roles
TASK-141 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.1: Consolidated Print Layout | Add hidden print container <div id='shoshin-print-area'> to /my-rosters
TASK-142 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.1: Consolidated Print Layout | Implement JS function to build consolidated print HTML for one roster
TASK-143 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.1: Consolidated Print Layout | Render roster header in print view (Clan Name, Ref ID, Points, Initiative, Honor, Masteries)
TASK-144 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.1: Consolidated Print Layout | Group roster items by class and support type in print view
TASK-145 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.1: Consolidated Print Layout | Aggregate MRBPA modifiers per build and cap display to 8 with overflow note
TASK-146 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.1: Consolidated Print Layout | Aggregate Abilities per build and cap display to 8 with overflow note
TASK-147 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.1: Consolidated Print Layout | Render stats table (melee, ranged, ATK, DEF, MOV, BOD, LDR, INI) in consolidated layout
TASK-148 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.1: Consolidated Print Layout | Render cost panel showing cost per unit, quantity, and line total
TASK-149 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.1: Consolidated Print Layout | Compute and render percentage of Clan Points per build in cost panel
TASK-150 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.1: Consolidated Print Layout | Create print-specific CSS for consolidated roster sheet layout
TASK-151 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.1: Consolidated Print Layout | Test consolidated print output in at least one browser print preview
TASK-152 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.2: Complete Print Layout | Implement JS function to build complete print HTML for one roster
TASK-153 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.2: Complete Print Layout | For each roster item, generate Q copies of the build block where Q is quantity
TASK-154 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.2: Complete Print Layout | Hide quantity field inside each complete print build block (assume per-unit)
TASK-155 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.2: Complete Print Layout | Reuse MRBPA, abilities, and stats layout from consolidated mode
TASK-156 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.2: Complete Print Layout | Test complete print view with unit entries that have large quantities
TASK-157 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.2: Complete Print Layout | Validate complete print layout remains readable across multiple pages
TASK-158 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.3: Print Mode Selector | Replace direct Print action with a selector UI (dropdown or modal)
TASK-159 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.3: Print Mode Selector | Wire 'Consolidated Print' option to consolidated print builder and window.print()
TASK-160 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.3: Print Mode Selector | Wire 'Complete Print' option to complete print builder and window.print()
TASK-161 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.3: Print Mode Selector | Clear and repopulate #shoshin-print-area before each print build
TASK-162 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.3: Print Mode Selector | Test both print modes from /my-rosters for multiple rosters
TASK-163 | Sprint 4 | Epic 6: Print & PDF System | Feature 6.3: Print Mode Selector | Verify that canceling print returns the user cleanly to /my-rosters
TASK-164 | Sprint 5 | Epic 5: Cascading Delete & Roster Removal | Feature 5.1: Asset Deletion Cascade | Add hook to detect deletion of Character or Support Asset WPForms entries
TASK-165 | Sprint 5 | Epic 5: Cascading Delete & Roster Removal | Feature 5.1: Asset Deletion Cascade | Within delete hook, query all relevant roster entries for cleanup
TASK-166 | Sprint 5 | Epic 5: Cascading Delete & Roster Removal | Feature 5.1: Asset Deletion Cascade | Parse roster_items_json for each roster
TASK-167 | Sprint 5 | Epic 5: Cascading Delete & Roster Removal | Feature 5.1: Asset Deletion Cascade | Remove any roster items whose assetEntryId matches the deleted asset
TASK-168 | Sprint 5 | Epic 5: Cascading Delete & Roster Removal | Feature 5.1: Asset Deletion Cascade | Recompute Clan Points totals for affected rosters after cleanup
TASK-169 | Sprint 5 | Epic 5: Cascading Delete & Roster Removal | Feature 5.1: Asset Deletion Cascade | Update roster_total_points field for each affected roster entry
TASK-170 | Sprint 5 | Epic 5: Cascading Delete & Roster Removal | Feature 5.1: Asset Deletion Cascade | Save updated roster entries back to WPForms
TASK-171 | Sprint 5 | Epic 5: Cascading Delete & Roster Removal | Feature 5.1: Asset Deletion Cascade | Test deleting a character used in multiple rosters and confirm cleanup
TASK-172 | Sprint 5 | Epic 5: Cascading Delete & Roster Removal | Feature 5.1: Asset Deletion Cascade | Test deleting a support asset used in multiple rosters and confirm cleanup
TASK-173 | Sprint 5 | Epic 5: Cascading Delete & Roster Removal | Feature 5.2: Roster Delete Action | Implement JS confirmation dialog for roster Delete button on /my-rosters
TASK-174 | Sprint 5 | Epic 5: Cascading Delete & Roster Removal | Feature 5.2: Roster Delete Action | Create AJAX endpoint to delete roster WPForms entry with permission checks
TASK-175 | Sprint 5 | Epic 5: Cascading Delete & Roster Removal | Feature 5.2: Roster Delete Action | On delete success, remove roster row and expanded row from DOM
TASK-176 | Sprint 5 | Epic 5: Cascading Delete & Roster Removal | Feature 5.2: Roster Delete Action | Test deleting multiple rosters sequentially to ensure stability
TASK-177 | Sprint 5 | Epic 7: QA & Final Polish | Feature 7.1: Full QA Pass | Verify all distances and movement values show inch symbol consistently across UI
TASK-178 | Sprint 5 | Epic 7: QA & Final Polish | Feature 7.1: Full QA Pass | Confirm Assign buttons are green, Edit buttons yellow, and Delete buttons red throughout
TASK-179 | Sprint 5 | Epic 7: QA & Final Polish | Feature 7.1: Full QA Pass | Test character creation, editing, and deletion flows end-to-end
TASK-180 | Sprint 5 | Epic 7: QA & Final Polish | Feature 7.1: Full QA Pass | Test support asset creation, editing, and deletion flows end-to-end
TASK-181 | Sprint 5 | Epic 7: QA & Final Polish | Feature 7.1: Full QA Pass | Test roster creation, editing, and deletion flows end-to-end
TASK-182 | Sprint 5 | Epic 7: QA & Final Polish | Feature 7.1: Full QA Pass | Test Daimyo assignment and replacement from /my-assets Assign modal
TASK-183 | Sprint 5 | Epic 7: QA & Final Polish | Feature 7.1: Full QA Pass | Test Daimyo constraint within /create-roster composer UI
TASK-184 | Sprint 5 | Epic 7: QA & Final Polish | Feature 7.1: Full QA Pass | Test consolidated print mode across several rosters
TASK-185 | Sprint 5 | Epic 7: QA & Final Polish | Feature 7.1: Full QA Pass | Test complete print mode and verify page breaks are acceptable
TASK-186 | Sprint 5 | Epic 7: QA & Final Polish | Feature 7.1: Full QA Pass | Test roster limits for Contributor and Author roles behave as expected
TASK-187 | Sprint 5 | Epic 7: QA & Final Polish | Feature 7.1: Full QA Pass | Perform full scenario: create assets, build roster, assign units, print, delete asset, and re-check rosters